PUBLIC BOARD MEETING

Date:	24 July 2024	Agenda item: 3.2 / Paper number: CM/07/24/32
Title of paper:	Listening Learning and Responding to Concerns Review (LLRC) – Evaluation and Update
Purpose of paper:	For approval / For discussion
Executive sponsor:	James Bullion and Joyce Frederick
Accountable Director:	(Dept Director) Helen Rawlings
Presenter(s) or lead person:	Helen Rawlings / Jillian Marsden
Purpose of paper: / To discuss and approve the 12-month evaluation of the LLRC review / To discuss performance progress against recommendations of LLRC review / To approve the approach for further work. / Recommendations: / The Board is asked to note the evaluation report and associated papers. / The Board is asked to approve the recommendations set out in the paper. The recommendations are: / Prioritise further work to provide focus and mitigate risk to delivery / Move further evaluation from 18 months to 24 months / Engage the independent panel members on further evaluation and assurance / Embed evaluation and outcomes of the aims of the review into CQC business planning / Accept the evaluation report recommendations / The Board is asked to approve the following for ongoing work aligned to the LLRC review and achieving the 10 aims: / Delegation of LLRC oversight to the Executive Team Committee via the Strategic Oversight, Performance, and Investment Committee (SOPIC). / Overview / The 12-month evaluation for the LLRC Review has been completed (Annex A) based on evidence and performance up to May 2024. The LLRC review set out to achieve 10 aims, with recommendations set out into the 5 key areas (workstreams) (Appendix A). The 10 aims of the review should be fully integrated into how CQC works and CQC’s culture to ensure outcomes and impact are achieved and embedded. / Work to complete the recommendations for the LLRC review has taken place concurrently with widespread transformation across CQC including ways of working, people structures, and technology. The impact of this transformation has affected the amount and pace of change delivered in response to the LLRC review and as such the overall progress and impact of changes made is not where we would like it to be. The importance of the LLRC review recommendations and achieving the 10 aims remains important and so continued focus and effort on further achievements and measuring and monitoring the impact this brings is essential. / The evaluation was a thorough examination of quantitative and qualitative information to assess the progress and impact of the LLRC at 12 months. Indicators from our CQC people survey were also used as part of the evidence examined for the evaluation. / The original independent panel members for the review have provided valuable feedback for the 12- month evaluation and points to consider for ongoing progress. They too were considerate of the context in which CQC have been trying to deliver the recommendations with some achievements highlighted, however there was disappointment with progress made and the impact this is having. Areas of further focus identified included the need to maintain focus and pace for the remaining recommendations, ensure scrutiny, accountability, good governance, and coordination across CQC, embed cultural change, and not lose sight of the importance of our approach to racism and becoming an anti-racist organisation. / Findings from the evaluation / There has been progress to deliver on the LLRC recommendations and an improved performance since the last report to CQC Board in February 2024. However, overall progress is not to the extent CQC originally anticipated. / At the time of the evaluation, recommendation completion was: / 19 (23%) met and closed / 23 (27%) close to target / 29 (34%) in progress / 12 (14%) very far from target or yet to start / 1 (1%) yet to be allocated / At the time of writing (July 2024) there has been further progress with an additional 8 recommendations met and closed. These are associated with ‘Learning from the tribunal’, and ‘How we listen to staff’, workstreams. Overall completion is now: / 27 (32%) met and closed / 18 (21%) close to target / 30 (35%) in progress / 9 (10%) very far from target or yet to start / Full performance reporting aligned to the evaluation can be found in Appendix B / July 2024 performance reporting can be found in Appendix C / Where recommendations are unable to progress, barriers include; the impact of the transformation programme including new ways of working and regulatory platform, the scale and pace of work required to deliver against the recommendations including people resources and capacity and financial investment, and a lack of clarity around leadership and governance of the programme. / At this stage, the impact of achieving the recommendations and aims is not clearly evident. More time will be required to continue progress and embed change to the ways of working and subsequent cultural change. It should be acknowledged that CQC are entering a recovery phase to improve the way it works and delivery regulation, identify and manage risk, encourage improvement and innovation, and improve the experience of CQC staff. The aims of the LLRC are fundamental to this recovery and should be used as an underpinning framework to achieve improvement. / Trajectory / Oversight of work in progress, work planned and work due to start has been mapped via workstream updates. These items have a firm plan for progress and/or form elements of the key areas of focus detailed further on in the paper. In the next 3 – 9 months it is anticipated that the following recommendations will be fully completed: / By 3 months (October) / Mechanism and process for discussing high risk whistleblowing cases / Reporting on timeliness and quality assurance of how concerns raised with us are dealt with / Ensuring best practice is embedded in organisational change / Reasonable adjustment tracking, integrating into onboarding, and improved timeliness. / Workshops to build capacity for embedded evaluation for each recommendation / By 6 months (January) / Gather equality demographics when people contact us / Standalone prescribed persons report / Measuring and quality assuring the timeliness of when workers concerns are responded to / Fully aligning Freedom to Speak Up policy and delivery to culture work / Training and support for managers to ask about reasonable adjustments sensitively and professionally with a minimum standard of skill and capability. / Ongoing evaluation criteria drawn up for each aim of the LLRC review and recommendations / Wider roll out of race anti-racist training for staff / 9 months (April) / Formally setting ongoing evaluation and outcomes in CQC business plans / Further considerations / The board are asked to approve the following for ongoing work aligned to the LLRC review and achieving the 10 aims: / ET has agreed the Strategic Oversight, Performance, and Investment Committee (SOPIC) to be the governance forum with oversight of the LLRC. SOPIC will report to ET. We will incorporate independent panel member involvement into a formal SOPIC subgroup for LLRC so that we strengthen the internal challenge on progress. / SOPIC will prioritise delivery and monitor performance. This should also include covering elements of the LLRC review recommendations where more focus is needed, or work is not progressing as expected: / The following key areas will need focus: / Our revised information of concern (including whistleblowing) process and further work required to embed this, train staff and ensure our systems are working well do deliver this consistently. / Progressing capturing peoples experience and feedback when they contact us / Capturing the appropriate equality data through our systems from people who contact us and share information. / Freedom to speak up reporting to Board / Ongoing culture work at CQC to ensure recommendations aligned to cultural change are considered and embedded. / Capacity review to enable response to provider risk / Continued work to ensure effective management of change / Ongoing performance reporting will take place and accountability reviewed and refreshed. / Review and clarification of ownership against recommendations and workstreams to provide a clear accountability structure from executive to delivery level. / Allocation of project support for further oversight, performance update and reporting, and evaluation work. / Ongoing reporting against recommendation and workstream to demonstrate progress and overall RAG score, barriers and mitigation to progress, timelines. / Integration of the 10 aims and relevant recommendations, their outcomes and impact, into CQC business planning to embed changes. / Further internal engagement updates to inform CQC staff of the conclusions of the evaluation, performance, and next steps. / Further evaluation / Evaluation will be embedded into ongoing work and an overall evaluation approach confirmed, against the 10 aims, to embed in business planning and monitoring. / The planned 18 month evaluation should be moved towards 24 months to capture impact of change against the 10 aims. / The independent panel members should be engaged for further evaluation and oversight of progress and impact. / Closure of LLRC Review / It was an initial LLRC review recommendation to formally close the LLRC review at the 12-month evaluation point. / Due to the conclusions of the evaluation, the impact of transformation, performance progress, and the further work now required to progress recommendations it is suggested that this formal closure and movement into business as usual be completed after the 24 month evaluation. This would conclude in early Q2 2025-26. / Ongoing evaluation processes are being embedded into workstreams and will directly influence the integration of the LLRC into CQC business plans. / Reporting to CQC Board / It is proposed that further reporting of progress takes place through SOPIC, Executive Team Meeting and formally into Board in 6 months.
Governance: / Strategic Oversight Performance and Investment Committee / Executive Team Meeting / Relevant committees and groups are engaged with at workstream and recommendation level by the relevant owners
Strategy: / Acceptance by CQC Board of the recommendations from the LLRC review took place in March 2023. / Recommendation actions and responsibilities were distributed to appropriate leadership across CQC in May 2023 / Work has commenced through FY23/24 and 24/25 to address the recommendations. / Elements of the LLRC review align with CQC strategy. / It is the intention to map further work against recommendations and aims into the formal CQC business plan.
Finance: / Financial resource will be required for the involvement of independent panel members work / Further financial resource will be required as prioritisation of further work takes place and requirements to deliver this work are clarified. Evaluation will require the continuation of research programme budget.
Risk: / There is a risk that people impacted by the findings in the LLRC review (CQC Staff, Flexible Workforce Staff, Providers, Public) continue to be negatively impacted by how CQC work if recommendations are not met. / There is a reputational risk of not delivering committed actions and responses in relation to the LLRC review in an appropriate timeframe. / There is a risk to progress against the recommendations and quality of how we work if resources and capacity are not allocated and created to undertake priority work.
People: / The confidence and competence of the CQC workforce has the potential to improve because of the recommendations of the LLRC review. / All staff and staff from a minority group or those with protected characteristics require the opportunity to continue to support and contribute to this work and actions from recommendations. / Staff experience of working at CQC has the potential to improve. / The experience and quality of service provided to the public and providers has the potential to improve