PUBLIC BOARD, 19 January 2022

TITLE: Closed Cultures summary narrative of progress

Executive Sponsor: Kate Terroni - Chief Inspector, Adult Social Care
Presenter: Mary Cridge Deputy Chief Inspector (ASC)
PURPOSE: FOR ASSURANCE

This paper is provided to enable the Board to fulfil their duties in relation to:

Monitoring the progress and delivery of strategic change programmes

PROPOSAL OR RECOMMENDATION

The purpose of this paper is to update Board and the public of progress made so far on the closed cultures project.

AIMS OF PROJECT

The ‘Closed Culture’ project has been underway since 2019. This summary provides an account of the project, as well as the context for the improvements that were made. By ‘Closed Cultures’ we mean services that are at a higher risk of poor care and abusive cultures. These are usually services that are located away from people’s communities, services that support people with communication difficulties, and with a lack of staff with the right training and expertise.

By the end of the project we wanted to ensure that we are more aware of the features of a closed culture and we know the risk factors that might lead to the development of one. That we can detect closed cultures and know which services might be more likely to develop such a culture. We wanted to be able to use a variety of tools including intelligence, inspection, surveillance and our engagement with people using services, families, providers, commissioners and partners. We wanted to be able to better prevent closed cultures from developing. We want to ensure we do not register services that do not provide the right care models. We promote best practice to providers and commissioners through national independent voice publications. Finally, that we can support providers to improve and we hold them to account. If people are unsafe and care being provided is not improving quickly enough then we will use our enforcement powers which could include placing restrictions on a service or cancelling the registration of a provider.
SUMMARY OF WHAT WE ACHIEVED

- We undertook our first full round of inspections to services that care for people with a learning disability, mental health condition and/ or autistic people inspections (2014-2017) – we highlighted that there were seven key areas that needed significant improvement – one of these was the use of restraint and segregation, and another was the physical environment in mental health hospitals. We knew that many services needed significant improvements, however the scale and severity of the problems were not as clear.
- In 2018 a story of a young woman who had been held in segregation (isolated in another area of the service) for over 20 months came to light and we were asked by the Secretary of State for Health and Social Care to conduct a review of restraint, segregation and seclusion across mental health hospitals in England. Families and advocacy groups came to together to highlight more cases of people across England being subject to high levels of restraint and restrictive practice, like segregation. Over the course of the review, families and other groups helped we shed light on some extremely poor care across mental health hospitals, especially for people with a learning disability and or autistic people. There were many extremely distressing stories and care published in both our interim report (May 2019) and our final report Out of Sight - Who Cares?, (October 2020) and people who had been in institutions for decades of their life. Our work in this report would not have been possible without the help of families and people in services.
- At the same time our interim report was published on Out of Sight – Who Cares in May 2019, a BBC Panorama programme aired on the care at a hospital in Durham, Whorlton Hall. The programme showed some people with a learning disability and autistic people being verbally and physically abused. Families came forward to say this was not an isolated incident. This greatly accelerated the need for change.
- Since then, significant work has been undertaken to improve the way we both see and regulate services that may be at risk of a ‘closed culture’. Two independent reviews were commissioned by us straight away following the Panorama documentary, by David Noble and Professor Glynis Murphy and alongside we set up our own ‘Closed Cultures’ project to begin work to make improvements. It is important to note that both in the Glynis Murphy review and our work, we found services that care for people with a learning disability and autistic people were at a higher risk of a ‘closed culture’ and we have focused on this group of people.
- The work we have done in this project has been either as a result of what people and their families have told us, or in co-production with them in building new methodologies and new narratives in the system about what needs to change. None of this work would have been possible without the input of our Expert Advisory Groups – both external and internal – made up of people who use services, families, providers, commissioners, national bodies, voluntary sector partners and our regulatory colleagues. Their knowledge and experiences shaped this work from start to finish.
- During this time, the country was also hit by the COVID-19 pandemic, which disproportionately affected people with a learning disability and autistic people – lack of visitation, staffing pressures as well as shielding made closed cultures more likely to occur.[1]
  [1] Coronavirus: lessons learned to date, Sixth Report of the Health and Social Care Committee and Third Report of the Science and Technology Committee of Session 2021–22, House of Commons Health and Social Care, and Science and Technology Committees, Sept 2021, p 100.
- The reviews and our own work found that improvements were needed in four key areas:

  - Better data on people’s experiences – the way we collect these and analyse these are key to building an improved regulatory approach and will help us better understand how services are performing. However, building this picture and this data takes time and is something we will continue to embed into our future regulatory approach.
  - Observation and flexibility – in services that are at a higher risk of closed cultures (e.g. they are far away from people’s homes and communities, care for people that have communication difficulties or who are non-verbal, are isolated) findings highlighted that data can only take us so far in these services as many people are not in a position to share their experiences.
  - Training for our inspectors and regulatory colleagues – both our internal review and the independent reviews concluded that our inspectors needed more support to do their jobs in these services. Whether that’s support to better understand and measure how well services are using communication tools through Talking Mats or PECs (Picture Exchange Communication System), or whether that is support to identify what a closed culture looks like and how to take regulatory action. Training has already been rolled out and will continue to be expanded for colleagues looking at these services.
  - The need for greater research into closed cultures – In Professor Murphy’s review she concluded that closed cultures was under researched and needed significantly more research to understand the factors that contribute to a poor culture becoming an abusive culture.
Summary of action taken as a result
We have taken action against each of these findings and recommendations, which are listed in the table below. As a summary, the main ways we are more equipped to both identify and take action on closed cultures are:

  - Better intelligence collection and analysis – We have improved our ability to collect and analyse data from people who may be receiving care in a closed culture service. We have done several targeted campaigns of our ‘Give Feedback on Care’ service which is an accessible online form for anyone to give feedback on the care they are receiving. All feedback is used to inform future inspection activity. We have created a set of indicators specifically to improve how we identify services that are at a risk of developing closed cultures. The first set of indicators was rolled out to inspectors at the end of 2021 and their effectiveness will be monitored. Between 01/01/2021 and 31/12/2021 there has been 20% more people coming forward with whistleblowing enquiries for services that care for a people with a learning disability and or autistic people and in the same period there has been a 25% increase in enforcement action.
  - Enhanced inspections - We know that to truly understand what’s going on, we must take time to understand the culture of the service. We have done this through increased observation on inspections, at different times of the day, whether that’s through our Short Frame Observation Framework for Inspection or Quality of Life tools, or whether that’s having more conversations with staff and people in the service – observation is key.
  - Training and awareness - Our colleagues and staff are more aware of closed cultures and the factors that lead to abuse – over 70% of our all staff are aware of closed cultures and understand how their team need to work differently. Initial training on how to identify and respond to closed cultures was rolled out to 2,000 operational colleagues and is a mandatory requirement for colleagues. In additional over 1,400 colleagues were given additional training when inspecting services that autistic people might be in.
  - Research into closed cultures – An international two-day research symposium to look in depth at how to better detect closed cultures with Professor Glynis Murphy was held on 13th and 14th October 2020. The findings of this informed the need for future research. A proposal to conduct more research into the factors that lead a poor culture into an abusive culture has been approved for commissioning by the Department of Health and Social Care’s Research and Development Committee.
Overall, we are confident that we have improved our ability to detect poor care for those in closed cultures over the past two years since the beginning of the project. Although there is undoubtably more work to be done to improve this, and to embed this into our future work, we have been able to take significantly more action against services that have poor cultures – this is evidenced by the significant amount of services we have restricted admissions on, closed or taken enforcement other action against in the past two years. We now have a Director level post that focuses on services that care for people with a learning disability and autistic people that will continue to have oversight of this agenda and embed it into everything we do. We are clear that the work does not stop here and this continues to be a priority for us.

KEY UPDATES

Glynis Murphy report recommendations	Update
Recommendation 1 – Data and accessibility	We have developed risk indicators for closed cultures and things that increase the likelihood of a service developing a closed culture. This has been embedded into our regulatory process. / We have produced a bespoke dashboard for closed cultures and services that care for people with a learning disability and or autistic people that is monitored regularly for risk and informs enforcement action.
Recommendation 2 – Unannounced inspections and increased out of hours inspections	Our closed cultures guidance includes the need for unannounced and out of hours inspections where there is a risk of a closed culture. Since April 2021 56% of our new learning disability and autism inspections have included some out of hours inspection activity.
Recommendation 3 - Abuse allegations, safeguarding alerts and whistleblowing events	We are working at improving our risk escalation process that will be taken forward in the new year for how we escalate issues more efficiently. This will be in collaboration between us and NHS England. This will also be embedded into our Future Regulatory approach that is currently being developed.
Recommendation 4 – Improved communication with service users	We have developed a suite of communication tools to better enable our inspectors to reach people who have communication difficulties. This includes training on PECS (Picture Exchange System), MAKATON and BSL (British Sign Language) as well as the continued piloting of Talking Mats. Further training is being rolled out to our regulatory colleagues in these areas. / We have developed the Quality of Life tool in partnership with the University of Warwick that supports our inspectors to better identify when effective care planning is taken place. This is specifically for people with a learning disability and or autistic people that have multiple needs. / We are currently working to improve the way we use advocates across the organisation, working with Voiceability and their network of advocates. In the future this will include training and other tools.
Recommendation 5 – The Use of Level 1 and Level 2 inspections	We have undertaken significant work on how we regulate services for people with a learning disability and or autistic people. The key to this is specialist skills and increased observation. We have recognised the importance of strong leadership on this issue to ensure the agenda is progressed at pace. Debbie Ivanova was appointed as the interim Deputy Chief Inspector for services that care for people learning disabilities and or autistic people. Debbie providers leadership, oversight and challenge to our regulatory work in these areas. / Some practical changes made to better understand the whole culture of a service include: / Visiting services more regularly at different times of the day, eg: handover periods, meal times, and evenings / Spending more time speaking to people who use services and their families and speaking to as many people that may visit or have contact with a service such as advocates, commissioners, visiting professionals
Recommendation 6 - CQC should not register services like Whorlton Hall, that are very isolated, in unsuitable buildings, with out-of-date models of care	We have developed an updated policy on how we registers services for people with a learning disability and or autistic people. The policy is called ‘Right Support, Right Care, Right Culture’. This sets out what we expect from these services and is applied to all of these services going forward and any new applications. / It is centred around: / The Right support: Model of care and setting maximises people's choice, control and independence / The Right care: Care is person-centred and promotes people's dignity, privacy and human rights / The Right culture: Ethos, values, attitudes and behaviours of leaders and care staff ensure people using services lead confident, inclusive and empowered lives. / We have been to court on a number of occasions in the last five years to challenge services that do not meet these requirements. In the majority of cases we won or the provider withdrew.
Recommendation 7 – Ratings when services are using restrictive practices	We have undertaken work as per recommendation 1 to improve the way we collect and analyse data for services that may have a risk of a closed culture. This includes having an indicator for ‘restraint’ that feeds into the risk profile of a service. / We have also undertaken an interim progress report on ‘Out of Sight: Who Cares?’ which highlights the need for stronger system action to reduce the use of restraint across these services.
Recommendation 8 – Ratings when services cannot show how they support whistleblowing and reporting of concerns	We are currently updating the way our regulatory approach works as an organisation, this is in line with our new strategy and ‘future regulatory model’. A core part of this new approach will update the way we rate services, to become more intelligence and data driven, and use a wider pool of data sources in our judgements. This includes improving the way we hear from people who use services and using their voices to inform our regulatory action.
Recommendation 9 – Group Home Culture Scale	We are currently looking at how we could incorporate the Group Home Culture scale into our approach.
Recommendation 10 – Quality of Life tool	The Quality of Life tool pilot is a tool developed in partnership with the University of Warwick. The framework provides a structured and logical set of questions our inspectors might ask and that service providers should be asking themselves: / Who are the people the service is delivering support to? / What are their needs and aspirations? / Is the service meeting those needs and aspirations? / They help us understand whether the service is meeting the needs and aspirations of the people it is supporting. It points to potential sources of evidence with guidance about how to find the answers. / The tool is now used as a key part of inspecting services that care for people with a learning disability and autism.
Recommendation 11 – CQC should develop guidelines for when evidence of the quality of care (and the possibility of abuse) should be gathered from overt or covert surveillance.	We have RIPA powers (RIPA 2000 is legislation that regulates and balances human rights to a private life (Article 8). CQC has the powers to undertake both Directed Surveillance and Covert Human Intelligence Source (CHIS) but does not have the power to use Intrusive Surveillance so cannot use hidden cameras and listening devices in private spaces. / We have not previously used these powers. The powers were granted for the detection and prevention of crime and the protection of public health. CQC’s Executive Team and Board have now agreed that CQC can undertake work to develop our ability to use these powers, e.g. staffing, digital infrastructure. / We have also published guidance for inspectors on the use of surveillance by providers, and the use of CCTV. This was informed by internal and external engagement over the last 16 months and has been used to gather the views of stakeholders. The engagement looked at the legal and ethical issues alongside the benefits and risks arising from use of surveillance.
A note on David Noble recommendations	All recommendations from the David Noble report have been previously reported on and are underway.

CONTRIBUTIONS
 The following groups/people have been involved in forming this paper:

Groups/people	Involvement?	Feedback
HR	Not applicable
Finance	Not applicable
DHSC	Not applicable	Share 48 hours before
Executive Team	Choose an item.
Board Committee	Choose an item.
Executive Committee	Choose an item.
Trade Unions	Not applicable
Staff Networks	Not applicable
Other – please specify	Choose an item.